## Sheet1
2024 State Employee Charitable Campaign Timeline
Date | Activity | By
2024-01-01 | New Year's Day (State offices closed)
2024-01-08 | Request is posted for applications from charities interested in participating in the SECC as statewide federations or members. Note: 2024 is the 2nd re-certification application year of a three year cycle for all qualifying charity federation affiliate organizations. | SCM
2024-01-15 | Martin Luther King, Jr. Day (State offices closed)
2024-01-26 | Begin distribution of SECC 2024 campaign funds | LCM
2024-01-29 | Deadline for Local Campaign Managers to submit final 2023 campaign results report to State Campaign Manager, including list of leadership level donors | LCM
Week of February 6th | LEC MEETINGS: Review 2024 Local Campaign Manager applications, budget, and nominate LEC Chair | LEC
2024-02-05 | Statutory deadline for State Campaign Manager to submit final statewide campaign results reporting to Comptroller, SPC, and SAC | SCM
2024-02-05 | Deadline for 2024 Local Campaign Manager applications and proposed budgets to be sent to Local Employee Committee Chair | LCM
2024-02-12 | LEC Chair sends recommended 2024 Local Campaign Manager, budget, and 2023 Local Employee Committee roster, including Chair to the SPC for approval | LEC
2024-02-12 | Deadline for Local Campaign Managers to send any requests to produce local campaign materials to State Campaign Manager | LCM
2024-02-13 | Application announcement is posted by Local Campaign Managers for local charities interested in participating in the SECC. | LCM
2024-02-16 | Conference call for 2024 Local Campaign Managers - local charity application training and annual campaign planning | SCM, LCM
2024-02-19 | Presidents' Day (State offices closed)
2024-02-22 | Application deadline for charities applying as Statewide SECC charities, including 25-word descriptions and contribution impact information | STATEWIDE CHARITIES
February 23 - March 10, 2024 | State Campaign Manager conducts administrative review of Statewide charity applications | SCM
February 23 - March 10, 2024 | State Campaign Manager notifies statewide charity federations of application review findings | SCM
2024-02-28 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine the SCM; review and approve 2024 local region names and boundaries; review and approve 2024 LCMs and budgets. | SPC
2024-03-02 | Texas Independence Day (Skeleton crew required at state offices)
2024-03-08 | Application corrections due from Statewide charity federations | STATEWIDE CHARITIES
2024-03-08 | State Campaign Manager opens statewide charity applications to State Policy Committee for eligibility review | SCM
2024-03-09 | SCM distributes contact list of LCMs approved for campaign year | SCM
2024-03-13 | SAC MEETING: Review proposed 2024 campaign materials and theme | SAC
2024-03-13 | SPC MEETING: 2024 SECC application review training, miscellaneous topics | SPC
March 13 - April 14, 2024 | State Policy Committee reviews statewide charity applications | SPC
2024-03-22 | Application deadline for charities applying as local SECC charities, including 25-word descriptions and contribution impact information | LOCAL CHARITIES
March 22- April 14, 2024 | Local Campaign Managers conduct administrative review of local charity applications | LCM
March 22- April 14, 2024 | Local Campaign Managers notifies local charities of application review findings | LCM
2024-03-29 | Good Friday (Optional state holiday)
2024-03-29 | First distribution of 2023 SECC funds to be finalized | LCM
2024-03-31 | Cesar Chavez Day (Optional state holiday)
2024-04-04 | SECC Workshop & Roundtable webinar for all SECC stakeholders | ALL
2024-04-15 | SECC Honorary Chair(s) request letters sent to: Governor, Lt. Governor, and Speaker of the House | SCM
April 15 - May 1, 2024 | Local Employee Committees review local charity applications | LEC
2024-04-23 | SPC MEETING: Determination of statewide charity eligibility, review and approve 2024 campaign materials, including any requests for locally produced materials; approve campaign theme(s) | SPC
2024-04-21 | San Jacinto Day (Skeleton crew required at state offices)
2024-04-24 | SPC submits 2024 SECC region names, boundaries, and LCM contact list to CPA | SCM
2024-04-24 | SCM notifies SWFs of eligibility decisions by SPC | SCM
2024-04-29 | SWF eligibility appeals due to SCM | STATEWIDE CHARITIES
2024-05-01 | State Campaign Manager distributes statewide charity application appeals to State Policy Committee for eligibility review | SCM
May 1 - 17, 2024 | State Policy Committee reviews statewide charity application appeals | SPC
2024-05-01 | Deadline for corrections to local charities' applications | LOCAL CHARITIES
Week of May 1st | Campaign ordering options made available to LCMs — incentives (via SCM) + print materials (via RJB) | SCM + RJB
Week of May 1st | LEC MEETINGS: LECs meet to determine eligibility for all local 2024 SECC applicants and discuss materials/incentive items ordering | LEC
2024-05-08 | Deadline for LCMs to send approval/denial letters to Local applicants (reasons for denial detailed) | LCM
2024-05-15 | Local eligibility appeals due to SCM | LOCAL CHARITIES
2024-05-15 | Directory charity listing of approved/denied Local Organizations due to SCM | LCM
May 15 - 24, 2024 | State Policy Committee reviews local charity application appeals | SPC
2024-05-24 | SPC MEETING: DEADLINE FOR FINAL APPEALS REVIEW + DECISIONS (statewide and local = final content for SECC materials) and campaign planning. | SPC
2024-05-24 | Deadline for SCM to submit finalized (Excel) spreadsheet of all approved 2024 charities (statewide and local) to print contractor for campaign materials production. | SCM
2024-05-27 | Memorial Day (State offices closed)
2024-05-30 | Deadline for ordering campaign materials (print + incentives) through centralized ordering | LCM
June 6 - 20, 2024 | Proofing + alterations + approval of 2024 campaign materials — by SWFs and LCMs | SWF, LCM
2024-06-21 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed. | SPC
2024-06-19 | Emancipation Day (Skeleton crew required at state offices)
June 24 - 26, 2024 | Review + approval of finalized 2024 campaign materials — by SCM | SCM
2024-06-27 | "Send to Print" deadline for centralized printed materials | SCM
2024-06-28 | Second distribution of 2024 SECC funds to be finalized | LCM
During July | SCM-provided online giving software training for all Local Campaign Managers | SCM, LCM
2024-07-04 | Independence Day
2024-07-05 | All centralized ordering printed campaign materials sent to printers | SCM
2024-07-19 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed | SPC
First week of August | Campaign materials delivered to Local Campaign Managers (centralized ordering) | SPC
August 1 - 31, 2024 | Employee campaign coordinator trainings in all local regions | LCM
2024-08-02 | Statewide online giving software training led by Statewide Campaign Manager, open to statewide campaign coordinators and local campaign coordinators from all regions | SCM
2024-08-09 | SPC MEETING & PLANNING RETREAT: Campaign planning and miscellaneous topics | SPC
2024-08-27 | LBJ Day (Skeleton crew required at state offices)
September 1 - October 31, 2024 | Annual State Employee Charitable Campaign (statutorily authorized time to ask state or higher education employees for a charitable payroll deduction) | ALL
2024-09-02 | Labor Day (Offices closed)
2024-09-06 | SPC MEETING: Campaign items and miscellaneous topics as needed | SPC
2024-09-15 | Rosh Hashanah (Optional state holiday)
2024-09-24 | Yom Kippur (Optional state holiday)
2024-09-30 | Third distribution of 2024 SECC funds to be finalized | LCM
2024-10-02 | Rosh Hashanah (Optional state holiday)
2024-10-11 | Yom Kippur (Optional state holiday)
2024-10-14 | SPC MEETING: Campaign items and miscellaneous topics as needed | SPC
2024-10-28 | Final campaign result/report template due to LCMs | SCM
2024-11-07 | Deadline for all online agencies to turn in all paper payroll deduction forms to their Local Campaign Manager for data entry into online software | LCM
2024-11-08 | Deadline for all non-online agencies to turn in all paper payroll deduction forms to their respective payroll offices for data entry | LCM
2024-11-08 | SPC MEETING: Approval of charity, SCM, and LCM applications for the next campaign year | SPC
2024-11-11 | Veterans Day (State offices closed)
2024-11-15 | Deadline for Local Campaign Managers to enter all paper payroll pledges (only for all online agencies). | LCM
2024-11-15 | Final payroll report due to CPA | SCM
2024-11-28 | Thanksgiving Day (State offices closed)
2024-11-29 | Day After Thanksgiving (State offices closed)
December 1, 2023 - January 22, 2024 | Prepare final campaign results reporting for SCM | LCM
2024-12-06 | Application announcement is posted by current LCMs for charities interested in serving as a 2024 Local Campaign Manager | LCM
2024-12-24 | Christmas Eve Day
2024-12-25 | Christmas Day (State offices closed)
2024-12-26 | Christmas holiday (State offices closed)
2024-12-30 | Final distribution of 2024 SECC funds | LCM
2025-01-01 | New Year's Day (State offices closed)
2025-01-08 | Request is posted for applications from charities interested in participating in the SECC as statewide federations or members. Note: 2025 is a full application year for all federations and affiliate charitable organizations. | SCM
2025-01-20 | Martin Luther King, Jr. Day (State offices closed)
2025-01-17 | SAC MEETING: Review proposed 2024 SCM campaign plan, timeline, and budget | SAC
2025-01-24 | Deadline for Local Campaign Managers to submit final 2024 campaign results report to State Campaign Manager, including list of leadership level donors | LCM
2025-01-24 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine SCM | SPC
2025-01-24 | Begin distribution of SECC 2024 campaign funds | LCM
* State Policy Committee and State Advisory Committee meeting dates and agenda subject to change
ECC | Employee Campaign Coordinator
LCM | Local Campaign Manager
LEC | Local Employee Committee
LOCAL CHARITIES | Local Charity Federations and Unaffiliated Charities
SAC | State Advisory Committee
SCM | State Campaign Manager
SPC | State Policy Committee
STATEWIDE CHARITIES | Statewide Charity Federation
Note on A11: gbennett: By law, the state campaign manager shall ensure that the state policy committee, the state advisory committee, and the comptroller receive the statewide campaign report not later than February 5th of the calendar year following the calendar year in which the campaign covered by the report ended. If February 5th is not a workday, then the first workday after February 5th is the deadline.